Grand Plan & Best-Result Pipeline
Bangla Cyberbullying Detection Research Paper

Target outcome: a benchmark + method paper strong enough for serious Q1 journal / top conference submission.

Core strategy: build a multi-source Bangla cyberbullying benchmark, add a new hard annotated slice, fine-tune BanglaBERT + MuRIL + XLM-R/IndicBERTv2, and use a multi-task ensemble that is tested across source, script, and domain shift.

1. Grand Plan

• Benchmark first: Merge the strongest public Bangla cyberbullying / abuse datasets into one unified schema instead of relying on a single dataset.

• Add new data: Annotate a new hard slice (recommended: 3k-10k comments) with Romanized Bangla, slang, sarcasm, indirect abuse, and platform diversity.

• Model more than binary: Predict harmful vs non-harmful, abuse type, and severity so the paper is richer and more useful than standard yes/no detection.

• Train the strongest encoders: Use BanglaBERT as the main backbone, then add MuRIL and XLM-R or IndicBERTv2 for transliteration and generalization.

• Win on evaluation: Show strong in-domain performance plus source-held-out, script-held-out, and external-dataset robustness.

• Make it reproducible: Release code, splits, annotation guidelines, and ablations so reviewers see a serious benchmark paper rather than a narrow model paper.

2. Execution Pipeline

| Stage | Module | What we do for best results |
| --- | --- | --- |
| 1 | Task design | Define 3 tasks: binary harmful detection, abuse-type prediction, and severity prediction. |
| 2 | Data build | Merge public datasets into one schema and add a new annotated hard slice with Romanized Bangla, slang, sarcasm, and multi-platform comments. |
| 3 | Preprocessing | Apply light normalization: Unicode cleanup, emoji mapping, repeated-character reduction, URL/mention masking, and Banglish normalization. |
| 4 | Data splits | Create random split, source-held-out split, script-held-out split, and external-test setup. |
| 5 | Baselines | Run TF-IDF + Logistic Regression / SVM, then BiLSTM or similar neural baseline. |
| 6 | Main models | Fine-tune BanglaBERT, MuRIL, and XLM-R or IndicBERTv2 with identical training settings. |
| 7 | Training tricks | Use class-balanced or focal loss, weighted sampling, layer-wise LR decay, mixed precision, 5-fold CV, seed averaging, early stopping on macro-F1, and threshold tuning. |
| 8 | Final system | Ensemble the transformer outputs using weighted logits averaging; test stacking with a small meta-learner only if it improves Macro-F1 consistently. |
| 9 | Evaluation | Report Macro-F1 as the main metric, then Micro/Weighted-F1, MCC, AUROC/AUPRC, confusion matrix, and class-wise breakdown. |
| 10 | Ablations & errors | Show single-model vs ensemble, binary-only vs multi-task, with/without new data, with/without normalization, and perform qualitative error analysis. |

3. Final Model Recipe

– Primary encoders: BanglaBERT + MuRIL + XLM-R or IndicBERTv2.

– Architecture: one model per encoder with 3 heads (binary, abuse type, severity).

– Loss design: combine class-balanced cross-entropy / BCE or focal loss depending on task imbalance.

– Optimization: layer-wise learning rate decay, warmup, mixed precision, 3-5 seeds, and 5-fold CV.

– Inference: weighted logits ensemble first; then test simple stacking as an optional upgrade.

– Selection rule: choose the system with the best average Macro-F1 and the best external robustness, not the highest single-split accuracy.

4. Practical Roadmap

| Phase | Output |
| --- | --- |
| Phase 1 | Collect datasets, map labels, write annotation guideline, and finalize taxonomy. |
| Phase 2 | Annotate the new hard slice and compute inter-annotator agreement. |
| Phase 3 | Run baselines and single-transformer models with consistent preprocessing and splits. |
| Phase 4 | Tune the ensemble, thresholds, and robustness settings; then run external evaluation. |
| Phase 5 | Prepare ablations, tables, error analysis, code release, and paper writing. |

Bottom line

Best-result pipeline in one line: merge data -> add new hard annotations -> light normalization -> robust train/test splits -> fine-tune BanglaBERT, MuRIL, XLM-R/IndicBERTv2 -> multi-task heads -> ensemble -> threshold tuning -> external robustness testing -> ablations -> paper.